## Configuration Management Matrix
[6 empty] | RPaM Ontology project maintenance configuration |  |  |  |  | Legend: bolded = initiator, red = pending, green = done, n/a = not applicable, blank cells = n/a because previous to the initiator task.
bolded = initiator, red = pending, green = done, n/a = not applicable, blank cells = n/a because previous to the initiator task.
Issue # | Issue URL | Issue status | Change Request | To be implemented in release version | MS vs RPaM model mapping | Conceptual Data Model | Governance and maintenance | UBL-2.2 XSD Schemas | EU Power Taxonomy | SP-IR Taxonomy | MorMeeConstraints Taxonomy | Code Lists | OWL-DL-TTL Examples | UBL Examples | SHACL graphs | SCHEMATRON RULES | Interoperability Testbed | DOCUMENTATION | RELEASE NOTES | TRANSITION PLAN | GitHub repository
1 | . | . | . | v1.1.0 | We have identified the need for an SP-IR, coming from the AT model: OA Friendly Name. We understand that this requirement is addressed to the eMandate Registry and reads likes this (free translation that needs to be checked by AT: This is an optional element and defines the name of the application that will be displayed to the representative when selecting the power. | The RPaM conceptual data model forsees this situation: the eMandate Request cater for the specification of SP-IR and Constraints, through the Criterion entity. | n/a | n/a | n/a | Define a new Information Requirement for this need. | n/a | n/a | Produce an example | Produce an example | TBD | TBD | TBD | Refer to in: 1. section about the eMandate Request 2. section about SP-IR | A new SP-Information Requirement has been added to the eMandate Request to specify the Application that will be used in the eMR. | n/a | update