## Configuration Management Matrix
[6 empty] | RPaM Ontology project maintenance configuration |  |  |  |  | Legend: bolded = initiator, red = pending, green = done, n/a = not applicable, blank cells = n/a because previous to the initiator task.
bolded = initiator, red = pending, green = done, n/a = not applicable, blank cells = n/a because previous to the initiator task.
Issue # | Issue URL | Issue status | Change Request | To be implemented in release version | MS vs RPaM model mapping | Conceptual Data Model | Governance and maintenance | UBL-2.2 XSD Schemas | EU Power Taxonomy | SP-IR Taxonomy | MorMeeConstraints Taxonomy | Code Lists | OWL-DL-TTL Examples | UBL Examples | SHACL graphs | SCHEMATRON RULES | Interoperability Testbed | DOCUMENTATION | RELEASE NOTES | TRANSITION PLAN | GitHub repository
1 | . | . | . | v1.1.0 | We have identified the need for an SP-IR, coming from the AT model: OA Friendly Name. We understand that this requirement is addressed to the eMandate Registry and reads likes this (free translation that needs to be checked by AT: This is an optional element and defines the name of the application that will be displayed to the representative when selecting the power. | The RPaM conceptual data model forsees this situation: the eMandate Request cater for the specification of SP-IR and Constraints, through the Criterion entity. | CREATE AN ISSUE WITH THIS SUBJECT AND COMMENT: SUBJEC-> Need for OA Friendly Name. COMMENT: AT's Request has this Information Requirement in the eMandate Request: "This is an optional element and defines the name of the application that will be displayed to the representative when selecting the power." (transalated from German with GoogleTranslator, please help with this, AT). Is this a general need for all MS or just for AT? We need to identify what is common and what is not, and try and find a way of "extending" the "core" common model for particular purposes. | n/a | n/a | Define a new Information Requirement for this need. | n/a | n/a | Produce an example | Produce an example | TBD | TBD | TBD | Refer to in: 1. section about the eMandate Request 2. section about SP-IR | A new SP-Information Requirement has been added to the eMandate Request to specify the Application that will be used in the eMR. | n/a | update
2 |  |  |  | v1.1.0 | We have identified the need to add a description of the Empowerment, coming from the AT model. | This element has been added to the conceptual data model. |  | n/a | n/a | n/a | n/a | n/a | Add this element to the ontology | n/a |  |  |  | Refer to in: 1. section about the eMandate Request |  |  | update
3 |  |  |  | v1.1.0 | Regarding "Mandate/Representative/CorporatePerson", we think that the need AT has is in reality to be able to access the organisation to which a person works for. Are we mistaken? | This element (relationship) has been added to the conceptual data model. |  |  | n/a | n/a |  |  | Add this element to the ontology | [7 empty] | update
4 |  |  |  | v1.1.0 | The delegationLevel goes to Empowerment | This property has been added to Empowerment. |  |  | n/a | n/a | [10 empty] | update
5 |  |  |  | v1.1.0 | A new constraint about "the power cannot be delegated" has been added to the GenericConstraint | n/a |  |  | n/a | n/a | A new constraint "non-delegation" has been added. | n/a | Produce an example | [7 empty] | update
6 |  |  |  | v1.1.0 | The model has been simplified. | rpam:Empowerment rpam:constraint ccev:CriterionProperty |  |  | n/a |  | n/a | n/a | Add this element to the ontology | [7 empty] | update
7 |  |  |  | v1.1.0 | eRR/id |  |  |  | n/a | n/a | n/a | n/a | Add this element to the ontology | [7 empty] | update
8 |  |  |  | v1.1.0 | Documentation need | n/a |  |  | n/a | n/a | n/a | n/a | [5 empty] | If a mandate is struck-off in the eMandate Registry, all the empowerments therein contained must change their statuses accordingly (we may need to come up with a new status named :CANCELLED_MANDATE_STRUCK_OFF |  |  | update
9 |  |  |  | v1.1.0 | :CANCELLED_MANDATE_STRUCK_OFF | n/a |  |  | n/a | n/a | n/a | add this element to the status taxonomy | [8 empty] | update
10 |  |  |  | v1.1.0 | rpam:Exception | n/a |  |  | n/a | n/a | n/a | n/a | Add this element to the ontology | [7 empty] | update
11 |  |  |  | v1.1.1 | Provide one dataset populated with exceptions. | n/a |  |  | n/a | n/a | n/a | n/a | Produce an example | [7 empty] | update